## Slide 1
KNOWLEDGE TRANSFER
PULSE
Who does what, on which work, and where
User roles and the RFI and NC flows | Activity catalog | Work location hierarchy

## Slide 2: What PULSE does
PULSE is the field inspection and quality app for construction sites. Solar is live; wind, BESS, infra, PSS and transmission line follow.
RFI
Request for Inspection. A contractor says work is ready and reviewers decide.
NC
Non-Conformance. Quality staff record work that falls short, the contractor fixes it.
WAM
Work Area Management. Maps each role to the part of the site they may act on.
Today's three topics
1 People and flows
2 Activity catalog
3 Work locations

## Slide 3: Eleven roles, one chain of assignment
Admin
Cluster Admin
Site Admin
Plot Admin
Project Manager
Execution Lead
Quality Lead
Contractor Manager
Execution Engineer
Quality Inspector
Contractor Incharge
each tier is assigned by the one above
PM assigns EL and QL. EL assigns CM and EE. QL assigns QI. CM assigns CI.
Online: seconds to log in
Offline PWA: minutes first load
Management User is view-only and sits outside WAM.

## Slide 4: What each tier may assign in WAM
Logged in as | May assign | Roles
Admin | Everything | 10
Cluster Admin | All but Cluster Admin | 9
Site Admin | All but Site and Cluster Admin | 8
Plot Admin | All but Plot, Site and Cluster Admin | 7
Project Manager | Execution Lead, Quality Lead | 2
Execution Lead | Contractor Manager, Execution Engineer | 2
Quality Lead | Quality Inspector | 1
Contractor Manager | Contractor Incharge | 1
Rule of thumb
Admin tiers assign every role below them. From Project Manager down, only the next tier.
Single-assignee rows
CI, QI and EE rows hold one person. A new assignment replaces the old one.

## Slide 5: RFI: the contractor asks, two reviewers decide
Happy path
CI
create + submit
›
EE
first review
›
QI
final review
›
Approved
by both
A QI rejection at page 1, then one resubmit
EE
approve
›
QI
reject page 1
›
CI
resubmit
›
EE
approve
›
QI
approve
Two ways to reject: from page 1 (the details) or from the checklist by marking an item Not OK.
Any rejection goes back to CI, and after a resubmit the RFI passes through EE again.
Nine combinations of who rejects and where are all supported.

## Slide 6: RFI rules worth remembering
Code and resubmits
Format RFI-<Work Location>-<Work Area>-CIV-<n>. A resubmit makes a new child record. The code changes only if location, area, package, work section or checklist changed.
Drafts autosave locally
Leaving the create form saves an In-Draft row in that browser only. A fresh login loses it.
A page-1 rejection frees the form
CI may change any first-page detail on resubmit. The old selections are released.
Reviewers are not vendor-scoped
EE and QI see every RFI in their Work Area, whichever contractor raised it.

## Slide 7: NC: quality raises it, the contractor fixes it
Resolved with one rejection by EE
Creator
raises NC
›
CI
root cause + fix
›
EE
reject
›
CI
resubmit
›
EE
approve
›
QI
close
Who creates
QI, EE, PM, EL and QL. Only QI can save a draft.
One reject toggle
A single OK or Not OK choice on review, opening as OK. EE and QI tick an acknowledgement.
Mandatory on create
Target Date for Closure, a captured photo, and a Defect Type from a list driven by location and activity.

## Slide 8: Where RFI and NC meet
Raise NC from an RFI
While reviewing a checklist, QI marks an item Not OK and ticks Raise NC. The RFI is rejected together with an NC linked to that item.
The resubmit gate
CI can open the RFI but cannot submit until every linked NC is approved by EE and QI. A rejected NC keeps the gate shut.
A pending NC also blocks new RFIs
No new RFI can be created for the same inspection checkpoint and work section until that NC is approved.

## Slide 9: The activity catalog, top to bottom
PACKAGE
Civil
SUB-PACKAGE
Piling (MMS, Inverter, LT Cable Hangers)
ACTIVITY
Piling - MMS (A.1.1)
SUB-ACTIVITY
Piling - MMS, per Table
CHECKPOINT
Pre Pour Inspection - Pile
CHECKLIST
Micro Pile Checklist
The location tree says where the work is. An RFI is raised where one sub-activity meets one place.

## Slide 10: Checkpoints unlock one at a time
1
Pre Pour Inspection - Pile
2
Pre Pour Inspection - Pile Cap
3
Post Pour Inspection
4
Epoxy Coating
5
Routine Testing
Checkpoint 2 needs checkpoint 1 approved by EE and QI, for the same work section.
Min. unit | Work section is | Example
Table | One table in the Work Area | R01-T71
Inverter | One inverter in the Work Area | I47
Block | The Work Area itself | BL01
Cross-activity rules
Table activities depend on Table ones at the same table, Inverter on Inverter. Block activities can depend on both, and then every table and inverter in the Work Area must be approved first.

## Slide 11: Work sections are used up, and SOs scope contractors
When a work section is consumed
Key is (sub-activity, checkpoint, work section).
Only deleting the RFI frees it.
A resubmit reuses it at no extra cost.
Out of sections? Change the Work Area, or keep the area and change the activity.
Service Orders
CI and CM are assigned in WAM with a Service Order.
Each vendor's SO is mapped to specific activities.
So two contractors can share a Work Area, each limited to their own activity.
EE and QI are not SO-scoped. SO mapping itself now lives in DRS.

## Slide 12: Four levels, picked top-down
CLUSTER
2
Gujarat, Rajasthan
›
SITE
5
Khavda, Mandvi, Mundra, Baiya, Bandha
›
WORK LOCATION
79
Also called Plot. Has a project type
›
WORK AREA
3,945
The leaf. RFIs are raised here
Project type is a column on the Work Location, not a tree level: solar 55, bess 9, infra 9, wind 3, pss 2, transmission line 1. Khavda holds 73 of the 79 locations.
Snapshot of 2026-08-28. The tree is authored in DRS and can change.

## Slide 13: Two paths through the tree
Solar: S05b, 69 areas
Gujarat › Khavda › S05b › BL01
Chart: 
| Culvert | Drain | Road | BL block
Work areas | 5 | 20 | 20 | 24
Every solar location has 20 roads, 20 drains, 5 culverts and a varying number of blocks. Block activities collapse to one work section named BL01.
Wind: WTG-Mandvi, 69 areas
Gujarat › Mandvi › WTG-Mandvi › MNP29
Chart: 
| MP-P | MNP | MP turbine
Work areas | 1 | 2 | 66
Wind areas are turbines only. Each has exactly one work section, named after the area, so one area carries one RFI per checkpoint.

## Slide 14: Who sees which slice of the tree
1 Cascade
Each dropdown shows only children of the parent chosen above it.
2 WAM
The tree is cut to what the user is mapped to. Two PMs can see different slices.
3 Service Order
Contractor roles see only areas where their SO is mapped.
Missing option?
First check the parent selection and the user's mapping before calling it a bug. The tree itself is edited in DRS, which syncs to PULSE.

## Slide 15
Good to know
Offline PWA roles (CI, EE, QI) need a few minutes on first load. Online roles open in seconds.
New users can log in straight away, with no manual database step.
SO Mapping in the sidebar hands off to DRS. A DRS login or page is expected.
A work section is used up per (sub-activity, checkpoint, work section).
A pending NC blocks new RFIs on the same checkpoint and work section.